## LogFrame
Result | Outcomes (Necessary steps to achieve the result) | TFAF Outputs (TFAF actions that contribute to the outcomes) | Indicators (To measure that a specific output is contributing to an outcome) | Sources and Means of Verification [SMV] (To measure progress of the indicators) | Risks (Outside of TFAF control but with potential to limit its contribution)
All TFA Category C notifications receive necessary support and are fully implemented | 1. Members are fully aware of TF needs | 1. Incentivize well developed up-to-date needs assessment. | 1. A recently updated or revisited needs assesment. | Primary SMVs Participant feedback WTO TF Committee Minutes Needs assessment results ABC notifications received TFAF Reports Information/feedback from Members Information/feedback from donors Information/feedback from international organisations Transparency notifications Secondary SMVs World Trade Reports Trade Policy Reviews (TPRs) World Bank Doing Business World Economic Forum Enabling Trade Report OECD TF Indicators TFAF website- information on implementation deadlines of Members TFAF Annual Report Academic research TFAF Grant Reports | Political - Changes in government - Insufficient political capital: e.g. TFA is an executive priority but TFA (or related provisions) not passed by Parliament - New laws and regulations not implemented - Political disengagement of donors - Lack of backing for notification process Technical - Insufficient supply of experts with necessary expertise to respond to requests for support - Problems with project fomulation (scope, detail, duplication, ...) - Requests out of sync with donor programming cycles - Turnover of Members' staff leading to delays in processes - Lack of engagement/response to technical requests by donor partners - Insufficient, sustainable or predictable funding throughout the life of the Facility - Technical training does not convert to political commitment through lack of internal communication or silos - Lack of demand by developing and LDC members - Overdemand - Projects implemented unsuccessfully - Outputs not embedded.
| 2. Member has notified all TFA commitments (Category A, B & C) | 2. Requirement for applicants to have notified. | 2. Notifications submitted recently (in 3 months leading up to grant application)
| 3. TF needs/category C notifications articulated in terms of viable technical assistance projects | 3. Award Project Preparation Grant | 3. Amount of Project Preparation Grant funding received and number of countries involved.
| 4. Needs matched with donor support | 4. Complete Expression of Interest process | 4. Expression of Interests identified donor. Members still requesting assistance after Expression of interest process completed.
| 5. Technical assistance projects successfully implemented | 5. Award Project Grant | 5. Project Grant funding received. Amount and number of countries.
| 6. Additional TFA provisions implemented | 6. Monitoring and evaluation of grants | 6. Are additional TFA provisions being implemented?

## TFAF Impact Monitoring
Activity | Outcomes | Outputs | Indicator | Source and means of verification | Risks or Assumptions | Additional information
Note on A1: TFAF: Name your activity in this column. List the same activity more than once if it will achieve more than one outcome or output or if you want to record more than one indicator, SMV or risk.
Note on B1: TFAF: Select from the list, the overall outcome that your activity will contribute to.
Note on C1: TFAF: Select from the list the output that your activity will generate and that will contribute to achieve the outcome. There should be a clear logical link between the output and outcome identified
Note on D1: TFAF: Select from the list the indicator which will be used to measure to what extent your activity has generated the output you have identified.
Note on E1: TFAF: Pick from the list to identify how you will measure the indicator. You need to choose an indicator that will, wherever possible, provide detailed, quantitative evidence that your activity has indeed achieved the output identified and has contributed to the outcome identified.
Note on F1: TFAF: Select from the list the risks or assumptions that threaten the successful completition of your activity, or that undermine the attainment of the output identified or the contribution to the outcome.
Note on G1: TFAF: Use this column to provide any other additional information to support the logical flow from the activity to the output, the contribution to the outcome, the indicator selected, the measurement of change of the indicator and the risks or assumptions identified. Feel free to add additional information, not foreseen in the drop-down lists.

## Data (hidden)
DO NOT EDIT
Outcomes |  |  | RisksAssumptions |  | SMVs
1. Aware of TF needs. |  |  | Changes in government |  | Participant feedback
2. Notification supplied. |  |  | Insufficient political capital: e.g. TFA is an executive priority but TFA (or related provisions) not passed by Parliament |  | WTO TF Committee Minutes
3. TF needs/category C notifications articulated in terms of projects. |  |  | New laws and regulations not implemented |  | Needs assessment results
4. Needs matched with donor. |  |  | Political disengagement of donors |  | ABC notifications received
5. Projects successfully implemented. |  |  | Lack of backing for notification process |  | TFAF Reports
6. TFA provision implemented |  |  | Insufficient supply of experts with necessary expertise to respond to requests for support |  | Information/feedback from Members
Outputs |  |  | Problems with project fomulation (scope, detail, duplication, ...) |  | Information/feedback from donors
1. Incentivize well developed up-to-date needs assessment. |  |  | Requests out of sync with donor programming cycles |  | Information/feedback from international organisations
2. Incentivize notification. |  |  | Turnover of Members' staff leading to delays in processes |  | Transparency notifications
3. Expression of Interest. |  |  | Lack of engagement/response to technical requests by donor partners |  | WTO World Trade Reports
4.Project Preparation Grant |  |  | Insufficient, sustainable or predictable funding throughout the life of the action |  | Trade Policy Reviews (TPRs)
5. Project Implementation Grant |  |  | Technical training does not convert to political commitment through lack of internal communication or silos |  | World Bank Doing Business
6. Monitoring and evaluation of grants |  |  | Lack of demand by developing and LDC members |  | World Economic Forum Enabling Trade Report
|  |  | Overdemand |  | OECD TF Indicators
|  |  | Projects implemented unsuccessfully |  | TFAF website- information on implementation deadlines of Members
|  |  | Outputs not embedded. |  | Academic research
TFAF Grant Reports
Needs | Notifications | PPG | EoI | PG | M_and_E
1. A recently updated or revisited needs assesment. | 2. Notifications submitted recently (in 3 months leading up to grant application) | 3. Amount of Project Preparation Grant funding received and number of countries involved. | 4. Expression of Interests identified donor. Members still requesting assistance after Expression of interest process completed. | 5. Project Grant funding received. Amount and number of countries. | 6. Are additional TFA provisions being implemented?